## Launch Roadmap
KIWIMATH v1 LAUNCH ROADMAP
Target: 6-week sprint to Play Store ¦ Scope: Grade 1, Topics 1-3, Android ¦ Updated: April 2026
Week | Task | Owner | Status | Dependency | Notes
W0 — COMPLETED — Design & Schema Phase
| Pydantic models v0.3 (question, events, RegionPack) | Tech | DONE | — | Hybrid schema with 3-axis localization
| FastAPI skeleton (/questions/next, /health) | Tech | DONE | — | In-memory content store, renderer
| Schema validator + safe eval | Tech | DONE | — | AST-based, no eval()
| 4 SVG generators | Tech | DONE | — | object_row_cross_out, dice, triangle, grid
| Flutter app skeleton (5 screens) | Tech | DONE | — | sign_in, home, question, explanation, celebration
| Firebase Auth + Firestore init | Tech | DONE | — | google-services.json wired
| 56 validated questions (Topic 1) | Academic | DONE | — | G1-COUNT-050 to G1-COUNT-086 + step-downs
| Concept DAG v1 (14 nodes) | Design | DONE | — | Reviewed, 2 nodes to add (patterns, time)
| Slot taxonomy v1 (38 slots) | Design | DONE | — | 9 categories, 6 co-dependency rules
| Event schemas v1 (3 events) | Design | DONE | — | attempt_recorded, mastery_updated, revisit_due
| UI mockup v4.1.1 (3 screens green-lit) | Design | DONE | — | Flutter-ready spec
W1 — FOUNDATION — Wire the core loop
| Adaptive engine v0: step-down routing | Tech | TODO | Schema done | CRITICAL PATH. Kid answers wrong → serve step-down → re-assess. This is the product moat.
| Cloud Function: mastery_recompute | Tech | TODO | Event schemas | Firestore trigger on attempt_recorded. Enforces monotonic shown_score invariant.
| Cloud Function: revisit_scheduler | Tech | TODO | mastery_recompute | Checks decay threshold + spaced repetition intervals after mastery update.
| Firestore security rules | Tech | TODO | — | Client writes attempts only. mastery + revisits server-write-only.
| Add edge_type to concept_graph schema | Tech | TODO | DAG review | hard_prereq / soft_prereq / strand_order. UI renders differently.
| Author Topic 2 questions (Arithmetic) | Academic | TODO | Schema done | Target: 40+ questions for add/sub within 10. Use CONTENT-AUTHORING-GUIDE.md.
W2 — FLUTTER — Rebuild screens from v4.1.1 spec
| Flutter: tap-to-remove manipulable lesson player | Tech | TODO | Adaptive engine | CRITICAL PATH. The three-state spec: answering → ready → confirm. Soft-cap shake on overshoot.
| Flutter: branching DAG home screen | Tech | TODO | edge_type schema | World map with clouds (not padlocks). Soft-prereqs accessible, hard-prereqs locked.
| Flutter: Kiwi companion + mascot emotions | Tech | TODO | — | 7 emotions (neutral, thinking, happy, encouraging, celebrating, waving, reading). SVG asset pipeline.
| Flutter: offline attempt queue | Tech | TODO | Firestore rules | Queue attempts locally → flush on reconnect with is_offline_flush=true. Client UUID idempotency.
| Build 10 more SVG generators | Tech | TODO | — | number_line, ten_frame, bar_model, part_whole, place_value_blocks, coin_set, clock_face, shape_identify, pattern_strip, comparison_bars
| Author Topic 3 questions (Shapes) | Academic | TODO | Slot taxonomy | Target: 30+ questions for shapes.2d_basic. Must use shape_2d + shape_real_world_example slots.
W3 — INTEGRATION — Connect everything
| Flutter ↔ Firestore: attempt recording | Tech | TODO | Manipulable, Cloud Fn | CRITICAL PATH. Full loop: kid answers → attempt written → mastery_recompute fires → shown_score updates → UI reflects.
| Flutter: celebration screen + collectibles v0 | Tech | TODO | Mastery Fn | Monotonic score reveal animation. K-2 collectible stamp on mastery milestone.
| Flutter: hint system ("Hmm, I'm stuck") | Tech | TODO | Step-down routing | One tap → Kiwi walks through it. No menus, no shame. Uses step-down questions.
| COPPA/GDPR-K consent flow | Tech | TODO | — | Parent email gate before child account. No PII in kid-writable fields. India DPDPA compliant.
| Add 2 DAG nodes (patterns.create_extend, measurement.time_hour) | Tech | TODO | DAG review | Fixes singleton regions. 14→16 nodes.
| Content QA: validate all 3 topics end-to-end | Academic | TODO | Topics 2+3 authored | Run content_tools.validate on full corpus. Check slot usage, step-down chains, distractor quality.
W4 — POLISH — UX, performance, edge cases
| Flutter: onboarding wizard (character pick + tier) | Tech | TODO | Home screen | 5-continent cast selection. Explorer tier default for Grade 1. First-run only.
| Flutter: progress tracking (non-shaming) | Tech | TODO | Mastery Fn | "4 days practiced!" with collectible stamps. No grey future days.
| Build remaining SVG generators (~15 more) | Tech | TODO | — | subtraction_cross_out, addition_combine, array_model, fraction_strip, tally_marks, etc.
| Performance pass: Firestore reads, image caching | Tech | TODO | Full loop working | Target: <200ms question load, <50ms attempt write. Cache SVGs locally.
| Accessibility pass: TalkBack, font scaling, contrast | Tech | TODO | All screens built | Android Accessibility Scanner. Min touch target 48dp. Color contrast 4.5:1.
| Content: author 20+ step-down variants per topic | Academic | TODO | QA pass | Step-downs are the moat. Each wrong answer path needs a scaffolded sub-question.
W5 — QA + SUBMISSION PREP
| Full integration test: fresh user → mastery → revisit | Tech | TODO | All systems | End-to-end walkthrough on physical Android device. Test offline→online flush.
| RevenueCat integration (freemium) | Tech | TODO | — | Free: Topic 1 (counting). Paid: Topics 2+ (arithmetic, shapes). Annual subscription.
| Play Store listing: screenshots, description, icon | Design | TODO | All screens polished | 5 screenshots across 3 screens. App icon: Kiwi with backpack.
| Privacy policy + Terms of Service | Tech | TODO | COPPA flow | Required for Play Store. No PII collection. Under-13 audience.
| Designed for Families compliance | Tech | TODO | Privacy policy | Google Play program for kids apps. Teacher-approved badge target.
W6 — LAUNCH
| Play Store submission (closed testing) | Tech | TODO | All QA green | Internal testing track first. 14-day review for Designed for Families.
| Set up Crashlytics + Analytics | Tech | TODO | — | Firebase Crashlytics for crash reports. Custom events for funnel analysis.
| Parent daily-summary push notification | Tech | TODO | Mastery Fn, FCM | Cloud Function aggregates daily mastery_updated events → FCM push to parent.
| Open beta → production rollout | Tech | TODO | Closed testing OK | Staged rollout: 10% → 50% → 100%. Monitor crash rate + ANR rate.
TOTAL: 12 tasks DONE ¦ 30 tasks TODO ¦ 3 CRITICAL PATH items ¦ 6 weeks to Play Store

## Critical Path
CRITICAL PATH — 5 items that gate everything else
# | Task | Week | Blocks | Why Critical
1 | Adaptive engine v0: step-down routing | W1 | Manipulable, hint system, full loop | This IS the product. Without step-down routing, it's just a quiz app. Every wrong answer must diagnose and scaffold.
2 | Cloud Function: mastery_recompute | W1 | Celebration, progress, revisits, parent notif | Server-enforced monotonic invariant. Without this, shown_score can drop and kids lose confidence.
3 | Flutter: tap-to-remove manipulable | W2 | Full integration loop | The pedagogical moat. Tap-to-remove replaces multiple choice. Three-state spec (answering→ready→confirm) is the core UX.
4 | Flutter ↔ Firestore: attempt recording | W3 | Everything downstream | The full loop: answer → attempt → mastery_recompute → UI update. Until this works, nothing is testable end-to-end.
5 | Content: 100+ questions across 3 topics | W1-W3 | QA, launch | Can't launch with 56 questions in 1 topic. Need arithmetic + shapes + step-downs. Academic cofounder's primary deliverable.

## v1 Scope Cuts
EXPLICIT SCOPE CUTS — What v1 does NOT include
Feature | Deferred To | Rationale
iOS app | v1.1 (Q3 2026) | Android first for India market. 85%+ Android share.
Parent dashboard (web) | v1.1 | Push notifications cover 80% of parent need. Dashboard is a nice-to-have.
Place value (tens/ones) | v1.1 | Needs number line manipulable not yet built.
3D shapes | v1.1 | Needs 3D rendering pipeline. 2D shapes sufficient for launch.
Data / picture graphs | v1.1 | Needs graph interaction widget. Low priority for Grade 1.
Money / coin identification | v1.1 | Needs region-specific coin image assets across 4 regions.
Non-standard measurement units | v1.1 | CBSE-specific. Not in Common Core or Singapore.
Postgres migration | v1.1 | In-memory content store is fine for 200 questions. Migrate when content exceeds 1000.
Grade 2+ content | v2.0 | Get Grade 1 right first. DAG is extensible.
RTL layout (Arabic) | v1.2 | Launch with en-IN + en-US. Arabic needs full RTL audit.
Teacher/school dashboard | v2.0 | B2C first, then B2B.
Social features (friend challenges) | v2.0+ | Privacy complexity with kids. COPPA risk.